REX ISOLDE low energy stage – adapted from the yellow ISOLDE upgrade report

| Goals | Development | Preliminary study | Investment items | Investment cost | Manpower | Time estimate |
| --- | --- | --- | --- | --- | --- | --- |
| Improved Efficiencies and higher intensities | New high performance cathode | - Design study and construction of a new electron gun | New cathode, new electron gun mechanical parts | 50 kCHF | 2 years of a PhD at CERN | 2005-2007 |
|  | High intensity beam trapping | - Tests - Numerical studies | New RF excitation generators and amplifiers | 15kCHF | 1 year of a PhD student or ½ year of postdoc | During 2006 |
|  | Improving the trap efficiency | - Tests - Numerical studies | Idem |  | ½ year of a PhD | During 2006 |
|  | Improving the differential pumping at the trap | - Study together with the vacuum group | Possibly 2 new turbo pumps 1000 l Collimators Gas purifying system | 50kCHF | 2 months of a PhD | During 2007 |
|  | Narrowing the charge state distribution in the EBIS | - Shell closures related tests - MPI-K Heidelberg preliminary studies for DR resonances | Variable electron energy Requires a new electron gun (see first point above) | 20kCHF | ½ year of a postdoc | 2006-2008 |
| Higher beam purity | Suppressing the isobaric contaminants from ISOLDE | - Tests at REXTRAP - Numerical studies | Possibly modified RF excitation generators and amplifiers | 10 kCHF | 1 year of a PhD student or ½ year of a postdoc | 2005 |
|  | Molecular beams | - Possible interesting studies in collaboration with chemists - New beam development tests | - | - | 4 months of a postdoc | 2005-2006 |
|  | Improving the vacuum system of the transfer line | - Design of the cold trap by the vacuum group | Cold trap mechanical parts, new roughing pump | 20 kCHF |  | 2005- 2006 |
| Better beam emittance | Cooling techniques in charge breeders | - Preliminary tests and studies by other group in the EURONS network - Theoretical/ numerical studies (ion/electron optics) - Mechanical design study - Tests | Positively charged particle source, modification of the current electrode scheme Gas injection into the EBIS | 0 to 70 kCHF depending on which methode to use | 1 year of a postdoc | 2006-2008 |
| Comparison of Techniques | EBIS-ECR techniques | - Tests of performances | - | - | ½ year of a postdoc | 2005-2006 |
|  | Beam cooling techniques – Penning trap and RFQ coolers | - Tests of performances | - | - | ½ year of a postdoc | 2005??-2006 |
| Miscellaneous | Development of beam diagnostics | - Detector electronics installation - Tests with radioactive beam | Electronics and MCA | 20 kCHF | 2 months Joakim’s PhD | 2005 |
|  | Slow extraction of the charge bred beam | - Tests of extraction schemes | - | - | 2 weeks of a postdoc | 2005 |

Total cost 2005: 50 kCHF  / 2006 : 85 kCHF / 2007-2008 : 120 kCHF