## Sheet1
REX Linac upgrade to 5.5 MeV/u in shutdown 2007/2008 (without ISTC collaboration). Prices in kCHF
construction phase and commissioning
| equipment cost | FTEs | time (months) | milestones
Work
Development of proper concept |  | 1 Phys. | 3 | design of all cavities done, beam transport to all targets calculated
Coordination of construction of the cavities |  | 0.3 Phys. | 36 | cavities assembled, aligned and vacuum tested, first low level measurements
Low level rf measurements |  | 1 Phys. | 12 | voltage distributions adjusted, all cavity parameters measured
Installation of cavities at ISOLDE |  | 2 Tech. | 3 | cavities installed, supports fixed, cooling water connected
Installation of magn. Lenses and power supplies |  | 1 Tech. | 6 | all magnets in beam line, beam line closed up to targets
Setup of add. beam diagnostic boxes |  | 1 Eng. | 3 | DB in beam line, locally controled
Alignment (incl. realignment of whole machine) |  | 2 Tech. | 1 | alignment finished, external alignment targets fixed to the tanks
Installation of vacuum system, vacuum local controls |  | 1 Tech. | 6 | reasonable pressure in cavities, remote ctrl. for vac. sys. present
Setup of lead tunnel |  | 2 Tech. | 3 | tunnel accessible with doors, light installed
Modification and installation of rf-amplifiers |  | 2 Eng. | 6 | first operation at high power levels
Layout of low level system, ll-module production |  | 0.3 Eng. | 12 | all modules present and tested
Installation and test of ll-systems |  | 0.5 Tech. | 3 | first closed loop operation
Cavity conditioning |  | 1 Eng. | 2 | stable operation at nominal power, X-rays outside tunnel o.k.
Concept for remote control system |  | 0.5 Eng. | 3 | design for control system of upgraded Linac
Profibus connections, setup of SIMATICs |  | 1 Tech. | 3 | read/write values directly from SIMATIC
Control applications for rem. Ctrl. System |  | 1 Tech. | 3 | control of magnets and rf-amplifiers from ctrl. Room
Commissioning of the Linac |  | 1 Phys. | 6 | transmission and beam spot at target o.k., stable operation of all components
Presentations, publications, reports, prep. of meetings etc. |  | 1 Phys. | 3 | commissioning results presented at LINAC2008 conference...
Material Costs
rf-amplifiers | 1000
resonator tanks (material and production) | 745
copper plating (tank drifttube structure) | 100
piston tuners, drifttube structure | 80
supports stands | 40
lead tunnel, material and construction | 200
low-level rf modules and SIMATIC crates | 95
electronics (vac.ctrl. SIMATIC, PCs, ADCs, Profibus) | 95
vacuum system | 200
magnetic lenses and power supplies | 310
additional beam diagnostic boxes | 50
Operation
operation /year
| running costs | FTEs
Linac supervision during experiments (status Jan. 2005) | 20 | 1.5 Eng.
Repairs, maintenance, optimisation (status Jan. 2005) | 60 | 0.5 Eng.